## Sheet1
2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | Schedule Feasibility
2023-09-20: Title Defense; 2023-09-22: RRL and Initial Research about the Approved Topic | Initialization and Feasibility | Date |  | September | October | November | December
2023-09-22: Company hunting related to approved topic | Initialization and research | 2023-09-20 | 2023-10-16
[16 empty] | Identification of tools that will be used | 2023-10-07 | 2023-10-16
[16 empty] | Paper prototype | 2023-10-17 | 2023-10-20
2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | create a simple encryption (test) | 2023-10-17 | 2023-10-20
RRL and Initial Research about the Approved Topic
Company hunting related to approved topic
2023-10-06: Start on Technopreneurship; 2023-10-07: Concept Planning; 2023-10-17: Use of python to create a simple encryption(Test) | First layer of encryption | 2023-10-21 | 2023-10-27
2023-10-07: Initial research to identify the tools that will be used in the project.; 2023-10-17: Paper prototype | Feasibility test | 2023-10-21 | 2023-10-27
Programming and Fusing APIs
2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 5 layers of encryption | 2023-10-28 | 2023-11-02
2023-10-22: Chapter 1 and Chapter 2; 2023-10-29: Chapter 1 and 2 Refinement and Continuation | Initial HTML/CSS design | 2023-10-28 | 2023-11-02
2023-10-22: Company hunting related to approved topic; 2023-10-29: At least 5 Layers of Encryption; 2023-11-03: Firebase Auth API (Facebook) | File upload to application (test) | 2023-10-28 | 2023-11-02
First Layer of Cryptography | [6 empty] | Initial HTML/CSS User Interface |  |  |  |  | Firebase Auth API (Google)
Feasibility Tests | [6 empty] | File upload to application(Test) |  |  |  |  | At least 3 Layers of Encryption
2023-11-03: Firebase Auth API (Google/OTP) | Firebase Authentication API (facebook) | 2023-11-03 | 2023-11-06
[16 empty] | Firebase Authentication API (google) | 2023-11-03 | 2023-11-06
2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | Firebase Authentication API (OTP google) | 2023-11-03 | 2023-11-06
Python backend connection to HTML/CSS front end | [5 empty] | Cloud upload | [6 empty] | Rename, Delete files
Database for Encryption key | [5 empty] | Finishing layers of encryption | [6 empty] | Finalization of System
2023-11-07: File Decryption; 2023-11-13: Implementing Periodic table of elements as cryptography technique; 2023-11-20: Search for individuals who test encryption | Python back end connection to HTML/CSS front end | 2023-11-06 | 2023-11-12
[16 empty] | Database for Encryption Key | 2023-11-06 | 2023-11-12
[16 empty] | File Decryption | 2023-11-06 | 2023-11-12
2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | Monetization, Debugging and Finalization
2023-11-23: Monetization | Cloud upload | 2023-11-13 | 2023-11-17
[16 empty] | Finishing first layers of encryption | 2023-11-13 | 2023-11-17
[16 empty] | Implementing Periodic table of elements as cryptography | 2023-11-13 | 2023-11-17
2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | Raname and delete files | 2023-11-20 | 2023-11-25
Monetization | [15 empty] | Finalization of system | 2023-11-20 | 2023-11-25 |  |  |  |  | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05
Refining and debugging the system | [15 empty] | Search for individuals who tests encryption | 2023-11-20 | 2023-11-25 |  |  |  |  | 2023-09-20: Title Defense; 2023-09-22: RRL and Initial Research about the Approved Topic
Company hunting related to approved topic
[16 empty] | Monetization | 2023-11-26 | 2023-12-23
2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | Finalization and debugging of system | 2023-11-26 | 2023-12-23
Chapter 3 | [15 empty] | Testing and Evaluation of the product | 2023-01-01 | [5 empty] | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21
Testing and Evaluation of the product | [22 empty] | 2023-10-06: RRL and Initial Research about the Approved Topic
Company hunting related to approved topic
Use of python to create a simple encryption (Test)
[23 empty] | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06